6. Event Risk Management Plan

EVENT NAME:	 Event

EVENT DATE:	        Event Date

Prepared by:	name

Version:  	1.00

Date:		date

# Introduction

This Event Risk Management Plan (ERMP) for Event Name has been developed with reference to the Risk Management Framework.

# Event Overview

The following event specific information provides context for the risk assessment and management plan contained in this ERMP:

## 2.1	Event Summary

| Event Name: |  |
| --- | --- |
| Event Type: |  |
| Event Objectives: |  |
| Event Organisers: |  |
| Event Dates / Times: |  |
| Event Location / Route: |  |
| Route Surface: |  |
| Event Itinerary: |  |
| Event History: |  |
| Expected Attendance: |  |
| Other Details: |  |
| Event Budget: |  |
| Event Management Plans, MOUs & reference docs: |  |

## 2.2	Event Stakeholders

| Event Coordinator: |  |
| --- | --- |
| Organising Committee: |  |
| Event Delivery Partners: |  |
| Local Councils: |  |
| Other Agency / Support: |  |
| Suppliers / Equipment / Contractors: | - First Aid - Event Medical Support - Catering - Transportation of riders and bicycles - Bike maintenance service - Mobile Toilets & Showers - Traffic control and parking - Communications - Lighting and generators |
| Volunteers / Marshalls: |  |
| Media: |  |
| Major Sponsors: |  |
| Other sponsors: |  |
| Participants |  |
| Other Stakeholders: |  |
| Refer Appendix 1 Event Stakeholder Contacts List |  |

## 2.3	Event Specific Requirements

Event Specific

Location Specific

## 2.4	Previous Event Learnings

Prior Event Learnings

Include any previous general event learnings, including:

Other Similar Event Learnings

# Risk Assessment

## 3.1	Event Risk Assessment

- The following event-specific risk assessment has been undertaken in accordance with Risk Management Framework – refer Appendix 2 and 3 for Event-Specific risk assessment criteria. (amend as required for specific event)

| Risk Category | Risk Event | Likelihood | Consequence | Risk Level | Risk Treatment Strategy / Plan | Likelihood | Consequence | Current Risk Level | Acceptable |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Participants |  |  |  |  |  |  |  |  |  |
| Participant ability to undertake event | Participants may not have the skills or fitness to complete the event in reasonable timeframe |  |  |  | Include information on expectations for fitness and ability in event information, prior to registration. Social media direction video and emailed. Send a pre-event information video to all participants. |  |  |  |  |
| Lost or missing persons | A participant is left stranded or lost on the rail trail |  |  |  | Include in rider briefings the protocol to follow if they abandon the event or become lost. Sweeper marshals behind the last riders to ensure no riders are left behind. Riders advised to carry navigation device and mobile phone. |  |  |  |  |
| Public Interactions | Public may inadvertently interfere with event |  |  |  | Social media , Facebook, to alert public users of the trail will be undertaken ahead the of the event weekend. |  |  |  |  |
| Incident Management | An event incident is not managed |  |  |  | Include an incident management process in the Event execution plan |  |  |  |  |
| Communications | Lack of accessibility between event organisers or volunteers creates inconvenience or actual incident |  |  |  | Include a communication plan in the Event Execution Plan |  |  |  |  |
| Health and Safety |  |  |  |  |  |  |  |  |  |
| Large number of participants | Congestion and inconvenience for participants |  |  |  | Set riders off in groups of 50. Include code of conduct in the rider briefing. Use council information means to advise the public that event is on. |  |  |  |  |
| Condition of rail trail | A section of the rail trail may be in poor condition |  |  |  | Include trail condition information in the rider briefings |  |  |  |  |
| Riders leaving the rail trail | Riders may become lost or trespass on private property |  |  |  | Include in rider briefing code of conduct on the trail, including awareness of private property. |  |  |  |  |
| Medical Emergency, including animal or insect bites. | Harm to participant |  |  |  | Riders disclose medical conditions and allergies on registration. Medic teams are present for the event, including overnight stops. Include emergency procedures in rider briefings. |  |  |  |  |
| Animals on the rail trail | Safety hazards or harm to participants |  |  |  | Include animal awareness in rider briefings, including magpie swooping. Medic teams present for the event. |  |  |  |  |
| Dehydration of rider | Harm to participants |  |  |  | Participants advised to carry adequate fluid and nutrition - water stations provided at nominated locations. First Aid Officers on site and contactable throughout the event. Medic teams present for the event. Event timing in July provides cooler conditions |  |  |  |  |
| Handling of luggage and bikes | Injury to participants |  |  |  | Include safe handling awareness in rider briefings Encouraged participants to keep luggage under 20kg, Send a pre-event information video to all participants |  |  |  |  |
| Commercial |  |  |  |  |  |  |  |  |  |
| Event cancellation | Event cancelation due to severe weather |  |  |  | Pay expenses and secure bookings as late as practically possible to limit losses. Timing of event in July lessons likelihood of extreme weather. Pre-plan a second possible event in case of postponement. Ensure Terms and Conditions clearly outline refund policies. Outline procedures of potential losses in MoU between Event Partner and organisation. |  |  |  |  |
| Weather or Climate |  |  |  |  |  |  |  |  |  |
| Severe wet weather before or during the event | Safety hazards or harm to participants |  |  |  | Monitor Bureau of Meteorology. Delay, postpone or cancel the event if conditions are unsuitable. Establish a communication means to all participants |  |  |  |  |
| Severe heat event | Safety hazards or harm to participants |  |  |  | Monitor Bureau of Meteorology. Include in rider briefings advice of staying hydrated. Medic teams present for the event. Sweep vehicles for picking up riders. Delay, cancel or postpone the event if the ambient temperature is extreme. |  |  |  |  |
| Bushfire | Harm to Participants |  |  |  | Monitor RFS bushfire alerts and bushfire mapping. Consult with the relevant fire and emergency services on the ground in case of potential impacting fire. Establish a communication means to all participants |  |  |  |  |
| Vegetation damage on the rail trail due to weather event | Safety hazards or harm to participants |  |  |  | Include awareness of debris on the trail and fallen vegetation in rider briefings, Check the rail trail before each morning departure. |  |  |  |  |
| Route and Trail *see app. 4 |  |  |  |  |  |  |  |  |  |
| Low route hazard | Cycling Incident, injury to participant. |  |  |  | Existing signage on the trail. Rider briefings will include advice on following signage. First Aid and Mobile Medic team on route |  |  |  |  |
| Medium route hazard | Cycling Incident, injury to participant. |  |  |  | Additional Signage at hazard points. Include trail hazards and road crossings. Rider briefing will highlight hazards. Mobile medic team on route. |  |  |  |  |
| High route hazard | Cycling Incident, injury to participant. |  |  |  | Additional signage and marshals on site at trail/road crossing. Rider briefing will highlight hazards. Mobile medic team on route. |  |  |  |  |
| Traffic control | Unauthorised Vehicles entering the rail trail or campsites creating hazard. |  |  |  | Existing signage and TMR and council vehicle controls. |  |  |  |  |
| Volunteers |  |  |  |  |  |  |  |  |  |
| Volunteers unclear on roles and responsibilities for event | Inconvenience for volunteers or participants |  |  |  | Volunteer briefings and information made available prior to the event. Establish communication means for all staff and volunteers. |  |  |  |  |
| Event Equipment |  |  |  |  |  |  |  |  |  |
| Event equipment not available | Inconvenience for volunteers or participants |  |  |  | An event equipment check list and means of transport in included in the event plan. |  |  |  |  |
| Suppliers |  |  |  |  |  |  |  |  |  |
| Catering not meeting standards or not meeting requirements for participants | Inconvenience or harm to participants. |  |  |  | Ensure that the catering service providers meet the Food Standards Australia New Zealand Safe Food Australia guidelines. Ensure gluten free, vegetarian, vegan dietary requirements are catered for by including dietary information on the event entry. Provide contingency meal quantity to allow for last minute registrations. |  |  |  |  |
| Event Transport | Inconvenience for volunteers or participants |  |  |  | Include transportation plan in the vent execution plan |  |  |  |  |
| Site Management |  |  |  |  |  |  |  |  |  |
| Environment management | Overnight campsite or rail trail is affected by refuse or damage to fauna or flora. |  |  |  | Waste management is in place for campsites. Include environmental awareness in rider briefings. |  |  |  |  |
| Location has insufficient capacity | Inconvenience for volunteers or participants |  |  |  | Overnight stops have been booked where possible Overnight public space to be cordoned off prior to the event. |  |  |  |  |
| Location has insufficient amenities | Inconvenience for volunteers or participants |  |  |  | Additional toilet and shower capacity will be brought on site. |  |  |  |  |
| Security | Inconvenience or harm to volunteers or participants |  |  |  | Overnight locked bike storage available |  |  |  |  |

## Corporate Risk Assessment

- The following corporate risk assessment has been undertaken in accordance with Risk Management Framework– refer Appendix 2 and 3 for Event-Specific risk assessment criteria.

| Risk Category | Risk Event | Likelihood | Consequence | Risk Level | Risk Treatment Strategy | Likelihood | Consequence | Current Risk Level |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Financial |  |  |  |  |  |  |  |  |
| Budget overspends | Insufficient participants to cover event expenses. |  |  |  | Monitor incoming registration numbers weekly. Aim to be self-sustaining in terms of costs and revenue. Secure grants and sponsorships to reduce overall expenses. Delay payment of event costs such as deposits as long as possible to limit losses in the event of cancellation. Develop effective Marketing and Promotional campaign. Cancel event if entries do not meet targets. |  |  |  |
| Reputational |  |  |  |  |  |  |  |  |
| Reputation | Complaints by residents, businesses or adjoining owners due to the event, reflect on organisation’s reputation. |  |  |  | Event carried out between daylight hours. Notification of event to be provided to residents and businesses prior to event as required. Site will be left clean. Participants encouraged bring own plates to reduce waste. Arrange bins through council and collection. Arrange recycle stations/bins. Volunteers' clean-up crew to ensure area is left as found. |  |  |  |
| Marketing & Comms |  |  |  |  |  |  |  |  |
| Event Participation | Marketing fails to attract participants |  |  |  | A marketing plan is in place for the event |  |  |  |
| Membership / Satisfaction |  |  |  |  |  |  |  |  |
| Participant Satisfaction | Participants not satisfied with event |  |  |  | The event has been planned based on previous events and lessons learnt from participant surveys and observations taken into consideration. |  |  |  |
| Relationships & Partnerships |  |  |  |  |  |  |  |  |
| Relationship between organisation and event partner | Failure to build partnership with event partner |  |  |  | A clear MOU established between organisation and Event Partner, with post-event joint review. |  |  |  |
| Advocacy |  |  |  |  |  |  |  |  |
| n/a to this event |  |  |  |  |  |  |  |  |

Risk Management Action Plan

The following risk management action plan has been developed to address the key risks requiring treatment for this event.

## 4.1	Pre-Event (Planning)

| Action | Responsibility | When | Status / Comment |
| --- | --- | --- | --- |
| MOU between event partners in place | Event Director |  |  |
| Ensure an Event Management Plan is developed | Project manager |  |  |
| Ensure an Event Execution Plan is developed | Project manager |  |  |
| Ensure an Event Marketing Plan is developed | Project manager |  |  |
| Ensure an Event Budget is established | Project manager |  |  |
| Ensure an Event Risk Management Plan is developed (This document) | Project manager |  |  |
| Ensure medical services supplier has an event plan | Project Manager |  |  |
| Ensure all vendors have been booked | Project manager |  |  |
| Ensure all sites have been booked | Project manager |  |  |
| Ride marshals identified | Ride Coordinator |  |  |
| Event information describes the required level of fitness and ability required. | Marketing Director |  |  |

## 4.2	During Event (Delivery)

| Action | Responsibility | When | Status / Comment |
| --- | --- | --- | --- |
| Ensure site specific route hazard mitigations are in place. | Ride Coordinator | During the ride | Rides may only take place once mitigations are in place (*appendix 4) |
| Ensure rider briefings are undertaken each day | Ride Coordinator | Prior to each ride departure | Rider briefings will be documented before the event. Content will include all risk treatments. Specific commentary: - Follow signs - Pay attention to any marshals on the trail or nearby - Pay attention to all signage, including road crossings. Some roads are 100km/h road and signposts show these. Dismount and check - Gullies – use caution |
| Ensure First Aiders are present | Ride Coordinator | During each ride | Rides may only depart if First Aid contingent is present. |
| Ensure the medic suppliers | Ride Coordinator | During each ride | Rides may only depart if the medic team is present. Event medical support for the event |
| Check weather forecast daily | Event Coordinator | Each morning | Ride Coordinator informed |
| Signage installed on route and crossings | Ride Coordinator | Each morning | Pending |

## 4.3	Post-Event (Debrief)

| Action | Responsibility | When | Status / Comment |
| --- | --- | --- | --- |
| Post event survey to participants | Project Manager |  |  |
| Post event report (part of TMR progress reporting) | Project Manager |  |  |

Consultation

The following people were consulted in formulating the risk assessment and risk management plan for this event:

| Name | Organisation |
| --- | --- |

Endorsement

| Position | Approver | Date | Comments |
| --- | --- | --- | --- |

APPENDIX 1: 		EVENT STAKEHOLDER CONTACTS LIST

| EVENT ROLE | KEY CONTACTS / DETAILS | ALTERNATE CONTACT | BACKUP / CONTINGENCY |
| --- | --- | --- | --- |
| Event Coordinator |  | Details in Event Execution Plan |  |
| Delivery Partner |  |  |  |
| Delivery Partner |  |  |  |
| Local Council Contacts |  |  |  |
| Other Agency / Support |  |  |  |
| Other Agency / Support |  |  |  |
| Other Agency / Support |  |  |  |
| Other Agency / Support |  |  |  |
| Other Agency / Support |  |  |  |
| Key Suppliers / Equipment / Contractors: |  |  |  |
| Volunteers / Marshalls: |  |  |  |
| Media / Comms: |  |  |  |
| Major Sponsors: |  |  |  |
| Minor sponsors: |  |  |  |
| Participants & Emergency Contacts |  |  |  |

APPENDIX 2: 		EVENT RISK MATRIX

|  |  |  | Consequences |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- |
|  |  |  | 1 | 2 | 3 | 4 | 5 |
|  |  | Descriptor | Insignificant | Minor | Moderate | Major | Extreme |
| Likelihood Level | A | Almost Certain | Low | Medium | Medium | High | High |
|  | B | Likely | Low | Medium | Medium | High | High |
|  | C | Possible | Low | Low | Medium | Medium | Medium |
|  | D | Unlikely | Low | Low | Low | Medium | Medium |
|  | E | Rare | Low | Low | Low | Low | Low |

APPENDIX 3: 		EVENT RISK LIKELIHOOD & CONSEQUENCE CRITERIA

| Likelihood | Definition (Qualitative estimates of probability) |
| --- | --- |
| Almost Certain | Risk is expected to occur in most circumstances |
| Likely | Risk will probably occur in many circumstances |
| Possible | Identified factors indicated the risk might occur at some time |
| Unlikely | Risk could occur at some time, but it is improbable |
| Rare | Risk may occur only in exceptional circumstances |

| Consequence | Definition |
| --- | --- |
| Insignificant | The consequences are unimportant or not material |
| Minor | The consequences are relatively unimportant or small scale |
| Moderate | The consequences are important or significant |
| Major | The consequences are very serious or very significant |
| Extreme | The consequences are extremely serious or disastrous |

Appendix 4: Reference documents

| Document | Link |
| --- | --- |
| Event Execution Plan |  |